## Weekly_MSYes
Initial_Site_ID | Site_ID | Map_ID | Site_ID_Status | Latitude | Longitude | Elev_Feet | Location | State_Province | Country | Landownership | Landowner2 | Landowner3 | Landowner4 | Install_Plan | Notes about Site | Installation_Status | Initial_Recon | Recon_Completed | Site_Constructed | Equipment_Installed | Data_Flow_Started | Station_Certified | Last_Visited | Release_Plan | Met_Package | Permafrost_Probe | Strong_Motion | Wind_Turbine
A19K | A19K-1 | A19K | Certified Site | 70.2043 | -161.0713 | 79 | Kasegaluk | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 220 AZ, 5V and Poor Signal @ 90AZ, 3V | New Install |  |  | 08/28/2017 | 2017-09-26 | 2017-09-26 | 2017-10-02 | 2018-08-17 | 2019 | Yes | Yes | No | Yes
A21K | A21K-6 | A21K | Certified Site | 71.3221 | -156.6175 | 18 | Barrow | Alaska | USA | USGS | NOAA |  |  | 2014 | Ownership is USGS with an overlapping easment by NOAA (NOAA ARM facility, Radio to fiber optic at DOE/ARM server | New Install |  | 7/2/2013 | 4/24/2014 | 2014-06-02 | 2014-06-22 | 2014-07-10 | 2017-08-04 | Adopted/Permanent | Yes | No | No | No
A22K | A22K-2 | A22K | Certified Site | 71.0033 | -154.9742 | 17 | Sinclair Lake | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 80 AZ, 4 V | New Install |  |  | 08/05/2017 | 2017-08-19 | 2017-08-19 | 2017-08-29 | 2018-08-17 | 2019 | Yes | Yes | No | Yes
A36M | A36M-2 | A36M | Certified Site | 71.9922 | -125.2617 | 263 | Sachs Harbor | Northwest Territory | Canada | First Nation | Parks Canada |  |  | 2014 | At Parks Canada Garage in center of village | New Install |  |  | 06/02/2013 | 2013-09-02 | 2013-09-10 | 2013-09-10 | 2015-08-19 | Adopted/Permanent | Yes | No | No | No
B18K | B18K-1 | B18K | Certified Site | 69.3641 | -161.8016 | 728 | Kokolik | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 220 AZ, 5 V and @ 90 AZ, 3 V | New Install |  |  | 08/27/2017 | 2017-09-29 | 2017-09-29 | 2017-10-02 | 2018-08-17 | 2019 | Yes | Yes | No | Yes
B20K | B20K-1 | B20K | Certified Site | 70.0079 | -157.1599 | 230 | Meade River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V and @ 250' 8V | New Install |  |  | 08/06/2017 | 2017-08-11 | 2017-08-11 | 2017-08-22 | 2018-08-16 | 2019 | Yes | Yes | No | Yes
B21K | B21K-1 | B21K | Certified Site | 69.6211 | -154.6128 | 302 | Ikpikpuk River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V | New Install |  |  | 08/10/2017 | 2017-08-14 | 2017-08-14 | 2017-08-29 | 2018-08-16 | 2019 | Yes | Yes | No | Yes
B22K | B22K-1 | B22K | Certified Site | 70.34 | -153.4196 | 144 | Teshekpuk Lake | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 80 AZ, 4 V and 240 AZ | New Install |  |  | 08/06/2017 | 2017-08-11 | 2017-08-11 | 2017-08-22 | 2018-08-16 | 2019 | Yes | Yes | No | Yes
C16K | C16K-1 | C16K | Certified Site | 68.2746 | -165.3436 | 350 | Lisburne Hills | Alaska | USA | Native Patent or IC | North Slope Borough |  |  | 2017 | North Slope Borough, BGAN Good Signal @ 230 AZ, 5 V | New Install |  |  | 08/26/2017 | 2017-08-26 | 2017-08-26 | 2017-08-29 | 2018-08-18 | 2019 | Yes | Yes | No | Yes
C17K | C17K-1 | C17K | Certified Site | 68.4753 | -163.1776 | 1627 | DeLong Mountains | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2017 | North Shore Borough, BGAN Good Signal @230 AZ, 2 V | New Install |  |  | 08/27/2017 | 2017-08-27 | 2017-08-27 | 2017-08-29 | 2018-08-18 | 2019 | Yes | Yes | No | No
C18K | C18K-1 | C18K | Certified Site | 68.6483 | -161.1943 | 2772 | Utukok River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 120 AZ, 10 V and @ 240 AZ, 8 V | New Install |  |  | 08/29/2017 | 2017-08-29 | 2017-08-29 | 2017-09-05 | 2018-08-18 | 2019 | Yes | Yes | No | Yes
C19K | C19K-2 | C19K | Certified Site | 69.1049 | -159.5874 | 2444 | Lookout Ridge | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 120 AZ, 10 V and @ 240 AZ, 8 V | New Install |  |  | 08/29/2017 | 2017-08-29 | 2017-08-29 | 2017-09-05 | 2018-08-17 | 2019 | Yes | Yes | No | Yes
C21K | C21K-1 | C21K | Certified Site | 69.1565 | -154.7832 | 1312 | Knife Blade Ridge | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 240 AZ, 10 V | New Install |  |  | 08/16/2017 | 2017-08-17 | 2017-08-17 | 2017-08-22 | 2018-08-16 | 2019 | Yes | Yes | No | Yes
C23K | C23K-1 | C23K | Certified Site | 69.836 | -150.6126 | 588 | Itkilik | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 80 AZ, 4 V | New Install |  | 7/4/2014 | 06/20/2016 | 2016-06-21 | 2016-06-20 | 2016-06-20 | 2018-07-17 | 2019 | Yes | Yes | No | Yes
C24K | C24K-1 | C24K | Certified Site | 69.72 | -148.7009 | 379 | Franklin Bluffs | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 90 AZ, 5 V | New Install |  | 7/5/2014 | 6/16/1201 | 2016-06-17 | 2016-06-17 | 2016-06-17 | 2017-09-07 | 2019 | Yes | Yes | No | No
C26K | C26K-1 | C26K | Certified Site | 69.9175 | -144.9122 | 458 | Camden Bay | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-ANWR, North Slope Borough, BGAN Good Signal @ 90 AZ, 5 V, Possible cell signal out of Pt. Thompson | New Install |  | 7/5/2014 | 06/24/2016 | 2016-06-24 | 2016-06-24 | 2016-06-24 | 2018-07-17 | 2019 | Yes | Yes | No | Yes
C27K | C27K-1 | C27K | Certified Site | 69.626 | -143.7114 | 1287 | Jago River | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System (ANWR), North Slope Borough. Site coordinates are ~250fteet from the reconned location. FWS gave approval for this relocation. | New Install |  | 7/5/2014 | 06/23/2016 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2018-07-17 | 2019 | Yes | Yes | No | Yes
C36M | C36M-2 | C36M | Certified Site | 69.3476 | -124.0706 | 66 | Paulatuk | Northwest Territory | Canada | First Nation |  |  |  | 2014 | At the village recreational center | New Install |  |  | 8/21/2013 | 2013-08-21 | 2013-09-02 | 2013-09-10 | 2014-07-09 | Adopted/Permanent | Yes | No | No | No
D17K | D17K-2 | D17K | Certified Site | 67.6988 | -163.0831 | 556 | Noatak River | Alaska | USA | BLM | State Selected (BLM) |  |  | 2017 |  | New Install |  | 7/2/2014 | 08/26/2017 | 2017-08-26 | 2017-08-26 | 2017-08-29 | 2017-08-26 | 2020 | Yes | Yes | No | No
D17K | D17K-1 | AK.RDOG | Certified Site-Existing | 68.0547 | -162.9049 | 170 | Eli River | Alaska | USA | Existing | State Selected (BLM) |  |  | 2015 Existing | At Red Dog Mine, BGAN Good Signal @ 230 AZ, 5 V, Cell coverage likely available with good antenna | Accepted As Is |  | 7/2/2014 | 06/20/2015 | 2015-06-20 | 2015-02-19 | 2015-04-30 |  | NA | No | No | Yes | No
D19K | D19K-2 | D19K | Certified Site | 68.4946 | -158.1151 | 2200 | Kuna River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 90 AZ, 10 V | New Install |  | 7/2/2014 | 08/18/2017 | 2017-08-18 | 2017-08-18 | 2017-08-29 | 2018-08-20 | 2019 | Planned | Yes | No | Planned
D20K | D20K-2 | D20K | Certified Site | 68.7132 | -156.6132 | 1893 | Etivluk River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 | BLM-National Petroleum Reserve, BGAN Good Signal @ 215 AZ, 10 V | New Install |  | 6/30/2014 | 08/16/2017 | 2017-08-18 | 2017-08-18 | 2017-08-29 | 2018-08-20 | 2019 | Yes | Yes | No | Yes
D22K | D22K-2 | D22K | Certified Site | 68.8799 | -152.6821 | 1745 | Ayiyak River | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2017 | North Shore Borough, BGAN Good Signal @ 110 AZ, 5 V | New Install |  | 7/6/2014 | 08/17/2017 | 2017-08-17 | 2017-08-17 | 2017-08-29 | 2018-07-18 | 2019 | Yes | Yes | No | Yes
D23K | D23K-1 | D23K | Certified Site | 68.9656 | -150.6807 | 1333 | Nanashuk | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 110 AZ, 5 V | New Install |  | 7/6/2014 | 06/19/2016 | 2016-06-20 | 2016-06-20 | 2016-06-20 | 2018-07-18 | 2019 | Yes | Yes | No | Yes
D24K | D24K-2 | D24K | Certified Site | 69.1532 | -148.8233 | 960 | Happy Valley | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 110 AZ, 5 V, Wifi signal active at site from "70 North" camp | New Install |  | 7/6/2014 | 6/15/2016 | 2016-06-15 | 2016-06-15 | 2016-06-15 | 2018-08-19 | 2019 | Yes | No | No | No
D25K | D25K-2 | D25K | Certified Site | 69.322 | -146.3751 | 2528 | Kavik River | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | North Shore Borough, BGAN Good Signal @ 90 AZ, 5 V | New Install |  | 7/5/2014 | 06/22/2016 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2018-07-17 | 2019 | Yes | Yes | No | Yes
D27M | D27M-1 | D27M | Certified Site | 69.243 | -140.9648 | 2939 | Malcolm River | Yukon | Canada | Parks Canada |  |  |  | 2017 | BGAN @140 degrees | New Install |  | 7/28/2014 | 08/20/2017 | 2017-08-20 | 2017-08-20 | 2017-08-29 | 2018-08-24 | 2019 | Yes | No | No | Yes
D28M | D28M-5 | D28M | Certified Site | 69.3286 | -138.7367 | 102 | Stokes Point | Yukon | Canada | Parks Canada | Military |  |  | 2017 | Stokes Point Early Warning Site BAR-B | New Install | 3/11/2015 | 08/14/2015 | 08/19/2017 | 2017-08-19 | 2017-08-19 | 2017-08-29 | 2018-08-24 | 2019 | Yes | No | No | Yes
E17K | E17K-1 | E17K | Certified Site | 67.082 | -161.8262 | 764 | Hotham Inlet | Alaska | USA | BLM |  |  |  | 2017 | BGAN good signal 100 Az, 08 V | New Install |  | 6/8/2014 | 07/28/2017 | 2017-07-28 | 2017-07-28 | 2017-08-01 | 2017-07-28 | 2020 | Yes | Yes | No | No
E18K | E18K-1 | E18K | Certified Site | 67.4213 | -160.6027 | 646 | Tukpahlearik Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal excellent @ 235 deg. Az. 15 deg V | New Install |  | 6/9/2014 | 07/28/2017 | 2017-07-29 | 2017-07-29 | 2017-08-01 | 2018-08-19 | 2020 | Yes | Yes | No | Yes
E19K | E19K-2 | E19K | Certified Site | 67.4572 | -157.2316 | 1447 | Redstone River | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal good @ 240 deg. Az. 8 deg V | New Install |  | 6/9/2014 | 7/21/2017 | 2017-07-21 | 2017-07-21 | 2017-07-24 | 2017-07-21 | 2019 | Yes | No | No | No
E20K | E20K-5 | E20K | Certified Site | 68.2575 | -156.1885 | 2843 | Nygu River | Alaska | USA | BLM | North Slope Borough |  |  | 2017 |  | New Install |  | 09/08/2015 | 08/16/2017 | 2017-08-16 | 2017-08-16 | 2017-08-29 | 2018-08-20 | 2019 | Yes | Yes | No | Yes
E21K | E21K-1 | E21K | Certified Site | 68.4414 | -153.9721 | 2083 | Killik River | Alaska | USA | Native Patent or IC |  |  |  | 2017 | North Slope Borough, BGAN Good Signal @ 240 AZ, 10 V | New Install |  | 6/30/2014 | 08/17/2017 | 2017-08-17 | 2017-08-17 | 2017-08-29 | 2018-07-18 | 2019 | Yes | Yes | No | Yes
E22K | E22K-1 | E22K | Certified Site | 68.1343 | -151.8132 | 2532 | Anaktuvuk | Alaska | USA | Native Patent or IC | North Slope Borough |  |  | 2016 |  | New Install |  | 6/30/2014 | 06/28/2016 | 2016-06-28 | 2016-06-28 | 2016-06-28 | 2018-07-18 | 2019 | Yes | No | No | Yes
E23K | E23K-3 | E23K | Certified Site | 68.0584 | -149.6163 | 3558 | James Dalton Mtn, Chandalar | Alaska | USA | BLM | North Slope Borough |  |  | 2016 | Chandalar Shelf Camp, Airport, Comm relay site at Chandler Shelf DOT yard | New Install |  | 06/13/2014 | 6/25/2016 | 2016-06-26 | 2016-09-15 | 2016-09-15 | 2018-09-18 | 2019 | Yes | No | No | No
E23K | E23K | TOLK | Certified Site | 68.6408 | -149.5724 | 2434 | Toolik Lake Research Station | Alaska | USA | BLM |  |  |  | 2014 | UAF Arctic Biology LTER Research Station | New Install | 10/4/2010 |  | 08/13/2011 | 2011-08-13 | 2011-08-13 | 2013-08-19 | 2018-04-26 | Adopted/Permanent | Yes | No | No | No
E24K | E24K-1 | E24K | Certified Site | 68.0748 | -148.4868 | 2781 | Your Creek | Alaska | USA | State Patent or TA | North Slope Borough |  |  | 2016 | DNR, BGAN signal good @ 110 deg. Az. 5 deg V | New Install |  | 6/11/2014 | 06/29/2016 | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2018-07-19 | 2019 | Yes | Yes | No | No
E25K | E25K-1 | E25K | Certified Site | 68.1206 | -145.5678 | 2124 | Arctic Village | Alaska | USA | Native Patent or IC |  |  |  | 2016 |  | New Install |  |  | 07/12/2016 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2018-10-19 | 2019 | No | No | No | No
E27K | E27K-1 | E27K | Certified Site | 68.1861 | -141.5951 | 2145 | Coleen River | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-ANWR | New Install |  | 6/13/2014 | 07/13/2016 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2019 | Yes | Yes | No | No
E28M | E28M-4 | E28M | Certified Site | 68.6043 | -139.5349 | 1555 | Babbage River | Yukon | Canada | Crown Land |  |  |  | 2017 |  | New Install |  | 08/14/2015 | 08/20/2017 | 2017-08-20 | 2017-08-20 | 2017-08-29 | 2018-08-24 | 2019 | Yes | No | No | Yes
E29M | E29M-2 | E29M | Certified Site | 68.3889 | -137.8969 | 1063 | Blow River | Yukon | Canada | Crown Land |  |  |  | 2017 | BGAN @ 130 degrees | New Install |  | 7/27/2014 | 08/19/2017 | 2017-08-19 | 2017-08-19 | 2017-08-29 | 2018-08-24 | 2019 | Yes | Yes | No | Yes
E31M | E31M-1 | CN.INK | Certified Site-Existing | 68.31 | -133.53 | 175 | Rampart House | Northwest Territory | Canada | Existing |  |  |  | 2015 Existing | Canadian National Network site | Accepted As Is |  |  | 02/28/1992 | 1992-02-28 | 2015-04-21 | 2015-04-30 |  | NA | No | No | No | No
F13K | F13K-1 | AK.TNA | Certified Site-Existing | 65.5606 | -167.924 | 257 | Diomede | Alaska | USA | Existing | Military |  |  | 2015 Existing | MIL-Dept of Air Force | Accepted As Is |  |  | 10/24/1998 | 2014-10-06 | 2014-10-12 | 2014-10-13 |  | NA | No | No | Yes | No
F14K | F14K-2 | F14K | Certified Site | 65.4742 | -166.3288 | 873 | Arctic Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal fair 240 deg. Az. 5 deg V | New Install |  | 6/7/2014 | 07/19/2017 | 2017-07-19 | 2017-07-19 | 2017-07-24 | 2017-07-19 | 2020 | Yes | Yes | No | No
F15K | F15K-1 | F15K | Certified Site | 65.7077 | -164.6483 | 1273 | North Star Ditch | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 6/7/2014 | 07/18/2017 | 2017-07-18 | 2017-07-18 | 2017-07-24 | 2017-07-18 | 2020 | Yes | Yes | No | No
F17K | F17K-1 | F17K | Certified Site | 66.442 | -161.2502 | 167 | Baldwin Peninsula | Alaska | USA | BLM |  |  |  | 2017 | BGAN signal excellent @ 230 deg. Az. 13 deg V | New Install |  | 6/8/2014 | 07/27/2017 | 2017-07-27 | 2017-07-27 | 2017-08-01 | 2017-07-27 | 2020 | Yes | Yes | No | No
F18K | F18K-1 | F18K | Certified Site | 66.6001 | -159.6514 | 89 | Selawik | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Selawik (Village of), FWS-National Refuge System, BGAN signal excellent @ 230 deg. Az. 10 deg. V | New Install |  | 6/8/2014 | 07/27/2017 | 2017-07-27 | 2017-07-27 | 2017-08-01 | 2017-07-27 | 2020 | Yes | Yes | No | No
F19K | F19K-2 | F19K | Certified Site | 66.8332 | -157.7728 | 528 | Shaleruckik Mtn | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 6/9/2014 | 07/23/2017 | 2017-07-23 | 2017-07-23 | 2017-08-01 | 2018-08-19 | 2020 | Yes | Yes | No | Yes
F20K | F20K-2 | F20K | Certified Site | 67.0486 | -155.7251 | 446 | Avaraat Lake | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN signal good @ 110 deg. Az. 6 deg. V | New Install |  | 6/10/2014 | 07/22/2017 | 2017-07-22 | 2017-07-22 | 2017-07-24 | 2017-07-22 | 2019 | Yes | Yes | No | No
F21K | F21K-2 | F21K | Certified Site | 67.2221 | -153.483 | 1958 | Alatna River | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal good @ 115 deg. Az. 8 deg. V | New Install |  | 6/10/2014 | 06/20/2016 | 2016-06-20 | 2016-06-20 | 2016-06-20 | 2018-07-19 | 2019 | Yes | No | No | Yes
F22K | F22K-2 | F22K | Certified Site | 67.5076 | -152.179 | 1791 | John River | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal weak @115 deg. Az. 8 deg V | New Install |  | 6/10/2014 | 6/21/2016 | 2016-06-21 | 2016-07-14 | 2016-07-14 | 2018-07-19 | 2019 | Yes | No | No | Yes
F23K | F23K-2 | AK.COLD | Certified Site-Upgraded | 67.2278 | -150.207 | 1227 | Coldfoot Broadband | Alaska | USA | Existing | Bureau of Land Management |  |  | 2014 Existing |  | Station Upgrade |  |  | 6/12/2014 | 2004-05-19 | 2014-06-17 | 2014-07-29 |  | NA | No | No | No | No
F24K | F24K-1 | F24K | Certified Site | 67.5187 | -147.8871 | 2416 | Squaw Lake | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal good @ 110 deg. Az. 5 deg. V | New Install |  | 6/11/2014 | 06/30/2016 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2017-06-18 | 2019 | Yes | Yes | No | No
F25K | F25K-2 | F25K | Certified Site | 67.5933 | -145.643 | 2835 | Christian River | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Venetie Indian and Neets Al Corporation | New Install |  | 6/13/2014 | 07/15/2016 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2017-06-20 | 2019 | Yes | Yes | No | No
F26K | F26K-2 | F26K | Certified Site | 67.6946 | -144.1455 | 2240 | Sheenjek River | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-ANWR, BGAN not verified, but should be good signal from east. | New Install |  | 6/13/2014 | 07/15/2016 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2017-06-19 | 2019 | Yes | Yes | No | No
F28M | F28M-T1 | F28M | Certified Site | 67.6136 | -139.8717 | 1850 | Old Crow | Yukon | Canada | First Nation |  |  |  | 2017 | Located at southern end of gravel pit away from pit activity | New Install |  | 08/11/2016 | 08/18/2017 | 2017-08-18 | 2017-08-18 | 2017-08-22 | 2017-08-18 | Adopted/Permanent | Yes | No | No | No
F30M | F30M-2 | F30M | Certified Site | 67.6106 | -135.7863 | 1358 | Barrier River | Northwest Territory | Canada | First Nation |  |  |  | 2017 | Crown, BGAN @ 140 degrees | New Install |  | 7/28/2014 | 08/22/2017 | 2017-08-22 | 2017-08-30 | 2017-09-05 | 2018-08-25 | 2019 | Yes | Yes | No | No
F31M | F31M-T1 | F31M | Certified Site | 67.441 | -133.7419 | 183 | Tsiigehtchic | Northwest Territory | Canada | First Nation |  |  |  | 2016 | DSL available through NWTel, Option to use visitor center connection-TBD, Cabling: Use same cable port as power (to be installed) | New Install |  | 8/14/2014 | 08/25/2016 | 2016-08-26 | 2016-08-22 | 2016-08-22 | 2017-04-01 | 2019 | Yes | No | No | No
G09K | G09K-1 | AK.GAMB | Certified Site-Upgraded | 63.7767 | -171.7008 | 10 | Gambell | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | FWS-National Refuge System | Station Upgrade |  |  | 02/23/2002 | 2002-02-23 | 2015-02-19 | 2015-04-30 |  | NA | No | No | Yes | No
G14K | G14K-1 | AK.ANM | Certified Site-Existing | 64.5653 | -165.3706 | 358 | Anvil Mountain | Alaska | USA | Existing | Military |  |  | 2015 Existing | National Patent or IC, Native Select, Private, MIL-Dept of Air Force | Accepted As Is |  |  | 06/21/2010 | 2010-06-21 | 2015-02-19 | 2015-04-30 |  | NA | No | No | No | No
G15K | G15K-3 | G15K | Certified Site | 64.9941 | -164.0386 | 817 | Niukluk | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN Signal Good 210 deg. 10 deg. V | New Install |  | 6/6/2014 | 07/16/2017 | 2017-07-16 | 2017-07-16 | 2017-07-24 | 2018-08-21 | 2020 | Yes | No | No | No
G16K | G16K-1 | G16K | Certified Site | 65.3936 | -162.3547 | 554 | Koyuk River | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR, BGAN Signal Good 110 deg. Az. 10 deg. | New Install |  | 6/6/2014 | 07/15/2017 | 2017-07-15 | 2017-07-24 | 2017-07-24 | 2017-07-30 | 2020 | Yes | No | No | No
G17K | G17K-1 | G17K | Certified Site | 65.5011 | -160.6514 | 1109 | Kiwalik Mtn | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  | 5/22/2014 | 07/12/2017 | 2017-07-13 | 2017-07-13 | 2017-07-20 | 2017-07-13 | 2020 | No | No | No | No
G18K | G18K-2 | G18K | Certified Site | 65.895 | -158.654 | 1588 | Tagagawik | Alaska | USA | BLM |  |  |  | 2017 | BGAN signal good @ 110 deg. Az. 13 deg. V | New Install |  | 6/6/2014 | 06/15/2017 | 2017-06-15 | 2017-06-20 | 2017-06-20 | 2017-06-15 | 2020 | Yes | No | No | No
G19K | G19K-4 | G19K | Certified Site | 66.1434 | -157.087 | 1283 | Purcell Mt. | Alaska | USA | BLM | State Selected (BLM) |  |  | 2017 | BGAN signal good @ 110 deg. Az. 13 deg. V | New Install |  | 6/6/2014 | 06/14/2017 | 2017-06-14 | 2017-06-20 | 2017-06-20 | 2017-06-14 | 2020 | Yes | Yes | No | No
G21K | G21K-3 | G21K | Certified Site | 66.5155 | -153.5058 | 1463 | Allakaket | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR, BGAN signal good @ 120 deg. Az. 10 deg. V | New Install |  | 6/11/2014 | 06/18/2016 | 2016-06-18 | 2016-06-18 | 2016-06-30 | 2017-06-17 | 2019 | Yes | No | No | No
G22K | G22K-3 | G22K | Certified Site | 66.9214 | -151.5073 | 672 | Bettles | Alaska | USA | AKDOT |  |  |  | 2016 | Site located behing Fire Department/City Hall. Site owned by DOT, building leased to the city. Final location to be chosen in the summer. | New Install |  | 03/08/2016 | 6/17/2016 | 2016-06-17 | 2016-06-18 | 2016-06-18 | 2017-06-18 | 2019 | Yes | No | No | No
G23K | G23K-1 | G23K | Certified Site | 66.7108 | -150.0239 | 2447 | Bonanza Creek | Alaska | USA | BLM | State Selected (BLM) |  |  | 2016 | BGAN signal good @ 110 deg. Az. 10 deg. V | New Install |  | 6/11/2014 | 06/16/2016 | 2016-06-16 | 2016-06-16 | 2016-06-30 | 2017-06-17 | 2019 | Yes | No | No | No
G24K | G24K-2 | G24K | Certified Site | 66.7004 | -147.4754 | 1651 | Beaver | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Yukon Flats, BGAN signal good @ 100 deg. Az. 10 deg. V, BGAN signal good @ 230 deg. Az. 10 deg. V | New Install |  | 6/12/2014 | 07/18/2016 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2018-06-20 | 2019 | Yes | Yes | No | No
G25K | G25K-2 | G25K | Certified Site | 66.7653 | -146.1013 | 479 | Bearman Lake | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Yukon Flats, BGAN signal good @ 100 deg. Az. 10 deg. V, BGAN signal good @ 230 deg. Az. 10 deg. V | New Install |  | 6/12/2014 | 7/16/2016 | 2016-07-18 | 2016-07-19 | 2016-07-19 | 2017-06-19 | 2019 | Yes | Yes | No | No
G26K | G26K-2 | G26K | Certified Site | 66.9498 | -143.7848 | 592 | Porcupine River | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System-Yukon Flats, BGAN signal good @ 100 Az., V 10 deg. | New Install |  | 6/14/2014 | 07/21/2016 | 2016-07-21 | 2016-07-22 | 2016-07-22 | 2017-06-19 | 2019 | Yes | Yes | No | No
G27K | G27K-3 | G27K | Certified Site | 66.8088 | -141.6549 | 2251 | Doyon Strip #3 | Alaska | USA | Native Patent or IC |  |  |  | 2016 |  | New Install |  | 6/14/2014 | 07/22/2016 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2018-03-22 | 2019 | Yes | Yes | No | No
G29M | G29M-1 | G29M | Certified Site | 66.9116 | -138.0223 | 1877 | Pine Creek | Yukon | Canada | Crown Land |  |  |  | 2017 | North Yukon Land Management Area - Johnson Creek IMA Zone IV, BGAN @ 140 degrees | New Install |  | 7/27/2014 | 08/17/2017 | 2017-08-17 | 2017-08-17 | 2017-08-22 | 2018-03-26 | 2019 | Yes | Yes | No | No
G30M | G30M-T2 | G30M | Certified Site | 66.9808 | -136.2216 | 2425 | tuh Zraii Nijik, Yukon-NWT Border | Yukon | Canada | Yukon Highways | Crown Land |  |  | 2016 | VSAT: Horizon SE 6 degrees | New Install |  | 8/9/2014 | 8/24/2016 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2017-04-01 | 2019 | Yes | No | No | No
G31M | G31M-1 | G31M | Certified Site | 66.9227 | -134.2708 | 200 | Satah River | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Jackfish Lakes IMA Zone II | New Install |  | 7/29/2014 | 08/22/2017 | 2017-08-22 | 2017-08-22 | 2017-08-29 | 2017-08-22 | 2019 | Yes | No | No | No
H16K | H16K-1 | H16K | Certified Site | 64.6379 | -162.239 | 709 | Elim | Alaska | USA | Existing | Native Patent or IC |  |  | 2017 |  | New Install |  |  | 07/15/2017 | 2017-07-21 | 2017-07-21 | 2017-07-24 | 2017-09-07 | 2020 | No | No | No | No
H17K | H17K-1 | H17K | Certified Site | 64.937 | -159.9126 | 1299 | Ungalik River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/22/2014 | 07/11/2017 | 2017-07-11 | 2017-07-11 | 2017-07-11 | 2017-07-11 | 2020 | Yes | Yes | No | No
H18K | H18K-1 | H18K | Certified Site | 65.1527 | -158.3633 | 1621 | Honhonsa River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/21/2014 | 06/16/2017 | 2017-06-16 | 2017-06-20 | 2017-06-20 | 2017-06-16 | 2020 | Yes | No | No | No
H19K | H19K-2 | H19K | Certified Site | 65.5276 | -156.4494 | 351 | Roundabout Mt | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Native Patent or IC, FWS-National Refuge System-Koyukuk | New Install |  | 5/21/2014 | 06/13/2017 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2020 | Yes | Yes | No | No
H20K | H20K-1 | H20K | Certified Site | 65.4924 | -154.8808 | 1686 | Anotleneega Mt. | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/21/2014 | 06/11/2017 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2020 | Yes | No | No | No
H21K | H21K-4a | H21K | Certified Site | 65.6571 | -152.805 | 1707 | Melozitna River | Alaska | USA | BLM |  |  |  | 2015 |  | New Install |  |  | 5/30/2015 | 2015-05-31 | 2015-06-04 | 2015-06-04 | 2017-06-22 | 2020 | No | No | No | No
H22K | H22K-3-1 | H22K | Certified Site | 65.8937 | -151.3773 | 1840 | Ishtalitna Creek | Alaska | USA | BLM |  |  |  | 2016 |  | New Install |  | 06/22/2013 | 6/15/2016 | 2016-06-15 | 2016-06-14 | 2016-06-14 | 2017-04-02 | 2020 | Yes | No | No | No
H23K | H23K-5 | H23K | Certified Site | 65.8251 | -149.5432 | 2024 | Repeater Hill | Alaska | USA | State Patent or TA |  |  |  | 2015 | DNR | New Install | 05/31/2014 | 06/15/2014 | 5/20/2015 | 2015-05-21 | 2015-05-21 | 2015-05-29 | 2018-03-20 | 2020 | Yes | Yes | No | No
H24K | H24K-3a | H24K | Certified Site | 65.8371 | -147.8781 | 2672 | Nodoor Dome | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 5/26/2015 | 2015-05-27 | 2015-05-28 | 2015-05-29 | 2018-06-20 | 2020 | Yes | No | No | No
H25K | H25L | H25L | Certified Site | 66.2669 | -145.819 | 492 | Birch Creek | Alaska | USA | Native Patent or IC |  |  |  | 2016 | Station moved from H25K on DOT land to this location on village land 150ft away | New Install |  |  |  | 2016-11-09 | 2016-11-10 | 2016-11-10 | 2018-03-21 | 2019 | Yes | Yes | No | No
H27K | H27K-9 | H27K | Certified Site | 66.2305 | -141.5265 | 2580 | Steamboat Mountain | Alaska | USA | BLM | State Selected (BLM) |  |  | 2016 |  | New Install |  | 06/25/2013 | 7/24/2016 | 2016-07-25 | 2016-07-25 | 2016-08-05 | 2018-03-22 | 2019 | Yes | Yes | No | No
H29M | H29M-1 | H29M | Certified Site | 66.2191 | -138.3689 | 1575 | Whitestone | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Whitestone River IMA Zone III | New Install |  | 7/25/2014 | 08/16/2017 | 2017-08-16 | 2017-08-16 | 2017-08-22 | 2017-08-16 | 2019 | Yes | Yes | No | No
H30M | H30M | EPYK | Certified Site | 66.3701 | -136.7191 | 717 | Eagle Plains | Yukon | Canada | Existing |  |  |  | 2014 |  | New Install |  |  | 10/10/2012 | 2012-10-10 | 2012-10-11 | 2012-10-15 |  | Adopted/Permanent | No | No | No | No
H31M | H31M-2 | H31M | Certified Site | 65.8052 | -134.3426 | 2105 | Peel River | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Snake River Restricted Use Wilderness Area, BGAN @ 140 degrees | New Install |  | 7/26/2014 | 07/15/2017 | 2017-07-15 | 2017-07-20 | 2017-07-19 | 2018-08-25 | 2019 | Yes | Yes | No | No
I17K | I17K-1 | I17K | Certified Site | 63.8864 | -160.695 | 344 | Unalakleet | Alaska | USA | Existing | Native Patent or IC |  |  | 2017 | Native Select | New Install |  |  | 06/09/2017 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2020 | No | Yes | No | No
I19K | I19K-2 | AK.GCSA | Certified Site-Existing | 64.7461 | -156.8792 | 130 | Ruby | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | AEC will rebuild using existing borehole-no TA requirement | Accepted As Is |  |  | 07/01/2015 | 2015-07-01 | 2015-07-02 | 2015-07-29 |  | NA | No | No | No | No
I20K | I20K-2 | I20K | Certified Site | 64.7962 | -154.4783 | 246 | Naaghedeneel ne tl'uh kk'aat | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Nowitna | New Install |  | 5/21/2014 | 06/10/2017 | 2017-06-10 | 2017-06-20 | 2017-06-20 | 2017-06-10 | 2020 | Yes | Yes | No | No
I21K | I21K-3 | I21K | Certified Site | 65.18 | -151.9822 | 844 | Tanana | Alaska | USA | Native Patent or IC |  |  |  | 2015 | Tanana Tribal Council | New Install |  | 5/15/2015 | 5/30/2015 | 2015-05-31 | 2015-06-01 | 2015-06-16 | 2017-06-08 | 2020 | No | No | No | No
I22K | I22K-1 | AK.MLY | Certified Site-Upgraded | 65.0308 | -150.7392 | 2677 | Manley Hot Springs | Alaska | USA | Existing | Native Patent or IC |  |  | 2014 Existing | Manley Hot Springs (Village of), Private | Station Upgrade |  |  | 9/10/2014 | 2009-08-05 | 2014-09-12 | 2014-10-03 |  | NA | No | No | Yes | No
I23K | I23K-4 | I23K | Certified Site | 65.1479 | -149.3603 | 489.5 | Minto, Yukon-Koyukuk | Alaska | USA | Native Patent or IC |  |  |  | 2014 | Minto (Village) | New Install |  |  | 9/12/2014 | 2014-09-13 | 2014-10-14 | 2014-10-20 | 2017-09-27 | 2020 | No | No | No | No
I24K | I24K-2 | POKR | Certified Site | 65.1171 | -147.4335 | 1644 | Poker Flat Research Range | Alaska | USA | State Patent or TA |  |  |  | 2014 |  | New Install |  |  | 10/02/2012 | 2012-10-02 | 2012-10-16 | 2012-10-17 | 2015-10-12 | Adopted/Permanent | No | No | No | No
I24K | I24K | IU.COLA | Certified Site-Existing | 64.8736 | -147.8616 | 650 | College Outpost | Alaska | USA | Existing |  |  |  | 2014 Existing |  | Accepted As Is |  |  | 02/05/1999 | 1999-02-05 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
I25K | I25K-1 | AK.PPD | Certified Site-Upgraded | 65.52 | -145.52 | 4278 | Central | Alaska | USA | Existing | State Patent or TA |  |  | 2016 Existing |  | Station Upgrade |  |  | 09/05/2011 | 2011-09-05 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
I26K | I26K-1-2 | I26K | Certified Site | 65.3064 | -143.1541 | 1108 | Coal Creek Mining Camp | Alaska | USA | National Park Service |  |  |  | 2015 | Yukon-Charley River, Description: S25 T6N R22E, Fairbanks Meridian | New Install |  |  | 09/12/2015 | 2015-09-12 | 2016-06-20 | 2016-06-20 | 2017-06-23 | 2020 | Planned | No | No | No
I27K | I27K-5 | I27K | Certified Site | 65.6035 | -141.6153 | 2868 | Kandik River | Alaska | USA | BLM |  |  |  | 2016 |  | New Install |  | 06/25/2013 | 07/25/2016 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2020 | No | Yes | No | No
I28M | I28M-2 | I28M | Certified Site | 65.4483 | -139.9355 | 3899 | Miner Creek | Yukon | Canada | Crown Land |  |  |  | 2017 | Crown, BGAN @ 140 degrees | New Install |  | 7/24/2014 | 07/12/2017 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2019 | Yes | No | No | No
I29M | I29M-T1 | I29M | Certified Site | 65.3609 | -138.3063 | 1974 | Ogilvie River Highway Camp, Dempster Highway | Yukon | Canada | Yukon Highways | Crown Land |  |  | 2015 |  | New Install |  | 8/15/2014 | 10/20/2015 | 2015-10-20 | 2015-10-20 | 2015-10-20 | 2018-03-26 | 2020 | No | No | No | No
I30M | I30M-1 | I30M | Certified Site | 65.2225 | -136.3767 | 4593 | Mt. Dempster | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Hart River Restricted Use Wilderness, BGAN @ 140 degrees | New Install |  | 7/25/2014 | 07/14/2017 | 2017-07-14 | 2017-07-14 | 2017-07-24 | 2017-07-14 | 2019 | Yes | Yes | No | No
J14K | J14K-1 | J14K | Certified Site | 62.7492 | -163.554 | 82 | Nanvaranak Lake | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | 05/30/2017 | 2017-05-30 | 408127 | 2017-05-30 | 2017-05-30 | 2020 | Yes | Yes | No | No
J16K | J16K-2 | J16K | Certified Site | 63.2842 | -160.6021 | 1076 | Anvik River | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/22/2014 | 06/06/2017 | 2017-06-18 | 2017-06-20 | 2017-06-20 | 2017-07-10 | 2020 | Yes | Yes | No | No
J17K | J17K-1 | J17K | Certified Site | 63.3965 | -159.0777 | 1060 | VABM Dome | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Innoko | New Install |  | 5/22/2014 | 06/07/2017 | 2017-06-19 | 2017-06-20 | 2017-06-20 | 2018-04-22 | 2020 | Yes | Yes | No | No
J18K | J18K-4 | J18K | Certified Site | 63.465 | -156.7154 | 1660 | Innoko River | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  |  | 06/02/2017 | 2017-06-02 | 2017-06-07 | 2017-06-07 | 2017-06-02 | 2020 | Yes | Yes | No | No
J19K | J19K-2 | J19K | Certified Site | 63.994 | -155.6214 | 1276 | Poorman | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  |  | 06/03/2017 | 2017-06-03 | 2017-06-07 | 2017-06-07 | 2017-06-03 | 2020 | Yes | Yes | No | No
J20K | J20K-2 | J20K | Certified Site | 64.1767 | -154.1467 | 994 | Nowitna River | Alaska | USA | BLM |  |  |  | 2015 |  | New Install |  | 09/22/2013 | 06/30/2015 | 2015-07-01 | 2015-07-02 | 2015-06-29 | 2017-06-04 | 2020 | No | No | No | No
J21K | J21K-1 | AK.CHUM | Certified Site-Upgraded | 63.8827 | -152.3152 | 927 | Lake Minchumina | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Station Upgrade |  |  | 07/03/2015 | 2015-07-03 | 2004-06-02 | 2015-02-20 |  | NA | No | No | No | No
J22K | J22K-1 | AK.BPAW | Certified Site-Existing | 64.1002 | -150.9848 | 1910 | Bear Paw Mountain | Alaska | USA | Existing | State Selected (BLM) |  |  | 2015 Existing |  | Accepted As Is |  |  | 05/13/2004 | 2004-05-13 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
J23K | J23K-1 | AK.NEA2 | Certified Site-Upgraded | 64.5928 | -149.0694 | 1476 | Nenana | Alaska | USA | Existing | Native Patent or IC |  |  | 2014 Existing | State Patent or TA, State Microwave | Station Upgrade |  |  | 05/01/2012 | 2012-05-01 | 2014-06-16 | 2014-06-17 |  | NA | No | No | No | No
J24K | J24K | AK.HDA | Certified Site-Upgraded | 64.4057 | -146.9407 | 437 | Harding Lake | Alaska | USA | Existing | State Patent or TA |  |  | 2014 Existing | State Select, Private, State Microwave | Station Upgrade |  |  | 09/30/2012 | 2012-10-01 | 2014-10-30 | 2012-10-05 |  | NA | No | No | No | No
J25K | J25K-6-1 | J25K | Certified Site | 64.613 | -145.3697 | 3114 | Salcha River | Alaska | USA | State Patent or TA |  |  |  | 2015 | This site is approximately 0.4 miles from the orginally propsed location 64.61377, -145.38504, but still within the DNR permit boundaries | New Install |  |  | 08/24/2015 | 2015-08-25 | 2015-08-25 | 2015-08-25 | 2017-04-01 | 2020 | Yes | No | No | No
J26L | J26L-5 | J26L | Certified Site | 64.501 | -143.5636 | 3753 | Joseph Creek | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  | 06/26/2013 | 09/10/2015 | 2015-09-11 | 2015-09-11 | 2015-09-11 | 2017-04-01 | 2020 | Yes | No | No | No
J27K | J27K-1 | US.EGAK | Certified Site-Existing | 64.7774 | -141.158 | 892 | Eagle | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/18/2006 | 2006-08-18 | 2015-02-19 | 2015-04-30 |  | NA | No | No | No | No
J29M | J29N | J29N | Certified Site | 64.4525 | -138.2164 | 3150 | Klondike Camp | Yukon | Canada | Yukon Highways | Crown Land |  |  | 2017 |  | New Install |  |  | 07/17/2017 | 2017-09-21 | 2017-09-21 | 2017-09-25 | 2017-09-21 | 2020 | No | No | No | No
J30M | J30M-1 | J30M | Certified Site | 64.5753 | -136.3304 | 4656 | Hart River | Yukon | Canada | Crown Land |  |  |  | 2017 | Peel River Watershed Land Management Area - Hart River Restricted Use Wilderness Area, BGAN @ 140 degrees | New Install |  | 7/25/2014 | 07/13/2017 | 2017-07-13 | 2017-07-13 | 2017-07-20 | 2017-07-13 | 2019 | Yes | Yes | No | No
K13K | K13K-1 | K13K | Certified Site | 61.9331 | -164.6555 | 670 | Kusilvak | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Hooper Bay (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/25/2014 | 05/31/2017 | 2017-05-31 | 2017-06-06 | 2016-06-06 | 2018-08-21 | 2020 | Yes | Yes | No | No
K15K | K15K-1 | K15K | Certified Site | 62.2938 | -161.5308 | 1135 | Wolf Creek Mountain | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/23/2014 | 05/29/2017 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2020 | Yes | Yes | No | No
K17K | K17K-2 | K17K | Certified Site | 62.7161 | -158.3014 | 1112 | Iditarod | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  |  | 05/15/2017 | 2017-06-03 | 2017-06-07 | 2017-06-07 | 2017-06-03 | 2020 | Yes | Yes | No | No
K19K | K19K-2 | AT.TTA | Certified Site-Existing | 62.93 | -156.01 | 2277 | Tatalina | Alaska | USA | Existing | Military |  |  | 2017 Existing | State Select, MIL-Dept of Air Force. Tsunami Warning Center site. | Accepted As Is | [7 empty] | NA | No | No | No | No
K20K | K20K-4b | K20K | Certified Site | 63.3569 | -154.07 | 1748 | Telida | Alaska | USA | State Patent or TA |  |  |  | 2015 | DNR | New Install |  |  | 06/30/2015 | 2015-06-30 | 2015-07-02 | 2015-06-29 | 2017-06-04 | 2020 | No | No | No | No
K21K | K21K-2 | AK.CAST | Certified Site-Upgraded | 63.4193 | -152.0682 | 1788 | Castle Rocks | Alaska | USA | Existing | National Park Service |  |  | 2016 Existing |  | Station Upgrade |  |  | 08/05/2006 | 2006-08-05 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
K22K | K22K-2 | AK.TRF | Certified Site-Upgraded | 63.451 | -150.2872 | 5529 | Thorofare Mountain | Alaska | USA | Existing | National Park Service |  |  | 2016 Existing | NPS-Wilderness Desig | Station Upgrade |  |  | 06/06/2003 | 2003-06-06 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
K23K | K23K-1 | AK.MCK | Certified Site-Upgraded | 63.7323 | -148.9349 | 5315 | McKinley Park | Alaska | USA | Existing | National Park Service |  |  | 2014 Existing | Private | Station Upgrade |  |  | 08/15/1998 | 1998-08-15 | 2014-10-02 | 2014-10-03 |  | NA | No | No | Yes | No
K24K | K24K-3 | K24K | Certified Site | 63.8036 | -145.7784 | 2375 | Donnelly Dome | Alaska | USA | Military | Bureau of Land Management |  |  | 2016 | Dept. of Defense-Lease Alaskacom/AT&T through BLM | New Install |  | 4/17/2015 | 04/13/2016 | 2016-04-13 | 2016-04-14 | 2016-04-20 | 2018-08-23 | 2020 | Yes | No | No | No
K25K | K25K-1 | AK.RIDG | Certified Site-Upgraded | 63.7407 | -144.8417 | 2612 | Independent Ridge | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Station Upgrade |  |  | 07/07/2015 | 2015-07-08 | 2007-01-07 | 2015-02-20 |  | NA | No | No | Yes | No
K26K | K26K-1 | AK.SCRK | Certified Site-Upgraded | 63.9769 | -143.9859 | 4530 | Sand Creek | Alaska | USA | Existing | State Patent or TA |  |  | 2014 Existing |  | Station Upgrade |  |  | 07/01/2007 | 2007-07-02 | 2014-07-29 | 2014-07-29 |  | NA | No | No | Yes | No
K27K | K27K-1 | K27K | Certified Site | 64.0292 | -142.0758 | 2400 | Chicken | Alaska | USA | State Patent or TA |  |  |  | 2014 | Colocated with PBO AC61 | New Install |  |  | 6/14/2014 | 2014-07-07 | 2014-07-31 | 2014-08-05 | 2017-07-04 | 2020 | No | No | No | No
K28M | K28M-2 | CN.DAWY | Certified Site-Existing | 64.07 | -139.39 | 2688 | Dawson City | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 10/03/1994 | 1994-10-03 | 2015-09-01 | 2015-09-01 |  | NA | No | No | No | No
K29M | K29M-T1 | K29M | Certified Site | 63.8433 | -137.5201 | 4485 | Barlow Repeater Site | Yukon | Canada | First Nation |  |  |  | 2016 | VSAT: Horizon SE 2 degrees | New Install |  | 8/17/2014 | 08/21/2016 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2018-08-25 | 2020 | Yes | No | No | No
L14K | L14K-1 | L14K | Certified Site | 61.3416 | -162.6829 | 135 | Kuka Creek | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | 05/27/2017 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2020 | Yes | Yes | No | No
L15K | L15K-1 | L15K | Certified Site | 61.678 | -161.4869 | 718 | Ungalak Mt. | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 05/23/2014 | 05/28/2017 | 2017-05-28 | 2017-05-28 | 2017-05-28 | 2017-05-28 | 2020 | Yes | Yes | No | No
L16K | L16K-1 | L16K | Certified Site | 61.7105 | -159.4747 | 745 | Owhat River to East | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 5/23/2014 | 05/13/2017 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2020 | Yes | Yes | No | No
L17K | L17K-3 | L17K | Certified Site | 62.1344 | -158.2972 | 1109 | Donlin | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  |  | 05/14/2017 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2018-04-20 | 2020 | Yes | Yes | No | No
L18K | L18K-4 | L18K | Certified Site | 62.2195 | -156.6886 | 1079 | Granit Mountain | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  |  | 05/10/2017 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2020 | Yes | Yes | No | No
L19K | L19K-1 | L19K | Certified Site | 62.1816 | -154.8543 | 1450 | White Mountain | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 06/19/2015 | 2015-06-20 | 2015-06-22 | 2015-06-30 | 2018-08-29 | 2020 | Yes | No | Yes | No
L20K | L20K-3 | L20K | Certified Site | 62.4787 | -153.8798 | 2208 | St John Hill, Farewell | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install | 6/9/2015 | 06/09/2015 | 08/16/2015 | 2015-08-17 | 2015-08-17 | 2015-08-17 | 2017-10-14 | 2020 | Yes | No | No | No
L21K | L21K-1 | AK.PPLA | Certified Site-Existing | 62.8968 | -152.187 | 4864 | Purkeypile | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Accepted As Is |  |  | 12/11/2002 | 2002-12-11 | 2002-12-12 | 2015-02-20 |  | NA | No | No | Yes | No
L22K | L22K-1 | AK.CUT | Certified Site-Upgraded | 62.4058 | -150.2625 | 1883.2 | Chulitna | Alaska | USA | Existing | State Patent or TA |  |  | 2014 Existing | State Select | Station Upgrade |  |  | 07/18/1986 | 1986-07-18 | 2014-05-16 | 2014-06-10 |  | NA | No | No | No | No
L23K | L23K-2 | AK.WAT1 | Certified Site-Existing | 62.8294 | -148.5508 | 2360 | Susitna Watana | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/12/2012 | 2012-08-12 | 2015-06-25 | 2015-06-25 |  | NA | No | No | Yes | No
L24K | L24K-1 | AK.DHY | Certified Site-Upgraded | 63.0753 | -147.376 | 5293 | Denali Highway | Alaska | USA | Existing | State Patent or TA |  |  | 2016 Existing |  | Station Upgrade |  |  | 06/24/2016 | 1992-08-21 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
L25K | L25K-1 | AK.PAX | Certified Site-Upgraded | 62.9704 | -145.4676 | 3770 | Paxson | Alaska | USA | Existing | State Selected (BLM) |  |  | 2015 Existing |  | Station Upgrade |  |  | 10/06/2003 | 2003-10-06 | 2003-07-20 | 2015-03-20 |  | NA | No | No | Yes | No
L26K | L26K-3 | L26K | Certified Site | 63.0254 | -143.3478 | 2133 | Log Cabin Wilderness Lodge | Alaska | USA | Private |  |  |  | 2014 | Mentasta (Village), Private | New Install |  |  | 7/22/2014 | 2014-10-22 | 2014-10-23 | 2014-10-31 | 2015-07-10 | 2020 | No | No | No | No
L27K | L27K-4 | L27K | Certified Site | 63.0618 | -141.8275 | 2470 | Northway | Alaska | USA | Military |  |  |  | 2014 | Native Patent or IC | New Install |  |  | 7/24/2014 | 2014-07-25 | 2015-03-18 | 2015-04-30 | 2015-04-18 | 2020 | No | No | No | No
L29M | L29M-1 | L29M | Certified Site | 63.109 | -138.129 | 3012 | Grand Valley Creek | Yukon | Canada | Crown Land |  |  |  | 2016 | Crown, BGAN @ 120 degrees | New Install |  | 7/24/2014 | 07/27/2016 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2018-08-28 | 2020 | Yes | No | No | No
M11K | M11K-1 | M11K | Certified Site | 60.3849 | -166.2011 | 8 | Mekoryuk | Alaska | USA | Existing | Native Patent or IC |  |  | 2017 | Mekoryuk (Village), FWS-National Refuge System | New Install |  |  | 05/24/2017 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2020 | No | No | No | No
M13K | M13K-1 | M13K | Certified Site | 60.4135 | -163.35 | 30 | Dall Lake | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Bethel (Village), FWS-National Refuge System-Yukon Delta | New Install |  | 5/24/2014 | 05/23/2017 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2020 | Yes | Yes | No | No
M14K | M14K-4 | M14K | Certified Site | 60.7515 | -161.96 | 62 | Bethel | Alaska | USA | Native Patent or IC |  |  |  | 2017 |  | New Install |  |  | 05/22/2016 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2020 | No | Yes | No | No
M15K | M15K-2 | M15K | Certified Site | 60.6947 | -160.6884 | 689 | Kasigluk River | Alaska | USA | FWS |  |  |  | 2017 | Alternate site, which is now the primary | New Install |  | 5/25/2014 | 05/21/2017 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2018-10-19 | 2020 | Yes | Yes | No | No
M16K | M16K-2 | M16K | Certified Site | 61.0224 | -158.9592 | 1292 | Timber Creek | Alaska | USA | State Patent or TA |  |  |  | 2017 | DNR | New Install |  | 5/25/2014 | 05/12/2017 | 2017-05-12 | 2017-06-05 | 2017-06-05 | 2017-05-17 | 2020 | Yes | Yes | No | No
M17K | M17K-2 | M17K | Certified Site | 61.4009 | -157.4375 | 1270 | Holitna | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  |  | 05/08/2017 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2020 | Yes | Yes | No | No
M18K | M18K-4 | M18K | Certified Site | 61.4907 | -155.8242 | 3110 | Stony River | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  | 9/07/2013 | 05/09/2017 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-10-14 | 2020 | Yes | Yes | No | No
M19K | M19K-1-1 | M19K | Certified Site | 61.9037 | -154.3915 | 1700 | Big River Lodge Airstrip | Alaska | USA | Private | State Patent or TA |  |  | 2015 | Big River Lodge | New Install |  | 9/7/2013 | 06/18/2015 | 2015-06-19 | 2015-06-30 | 2015-06-30 | 2017-10-14 | 2020 | No | No | No | No
M20K | M20K-3 | M20K | Certified Site | 61.8802 | -153.1318 | 3626 | Styx River | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  | 06/21/2015 | 06/20/2015 | 2015-06-21 | 2015-06-30 | 2015-06-30 | 2017-10-14 | 2020 | Planned | No | No | No
M21K | M21K-1 | AK.SKN | Certified Site-Upgraded | 61.9806 | -151.5292 | 1900 | Skwentna | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Station Upgrade |  |  | 05/15/2006 | 2006-05-15 | 2006-05-16 | 2015-02-20 |  | NA | No | No | Yes | No
M22K | M22K-1 | M22K | Certified Site | 61.7531 | -150.1205 | 187 | Willow | Alaska | USA | Private |  |  |  | 2015 | 26631 W. Bryce Cir., Willow, AK, Legal Description: Lot 5A Section 11, T19N, R5W, SM AK. | New Install |  | 4/17/2015 | 5/04/2015 | 2015-05-05 | 2015-05-12 | 2015-05-12 | 2018-08-30 | 2020 | No | No | No | No
M23K | M23K-8-TA.LNHD-1 | M23K | Certified Site | 61.7929 | -147.7262 | 1912 | Glacier View School | Alaska | USA | Private |  |  |  | 2016 |  | New Install |  | 01/28/2016 | 4/11/2016 | 2016-04-12 | 2016-04-13 | 2016-04-20 | 2018-08-22 | 2020 | Yes | No | No | Yes
M23K | M23K-7-AK.SCM | AK.SCM | Certified Site-Existing | 61.832 | -147.329 | 1050 | Sheep Mountain | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | State Microwave Site | Accepted As Is |  |  | 06/28/2009 | 2009-06-28 | 2015-10-25 | 2015-10-26 |  | NA | No | No | No | No
M23K | M23K-4 | AK.SAW | Certified Site-Upgraded | 61.807 | -148.3318 | 781 | Sawmill | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | Native Select, Private | Station Upgrade |  |  | 11/07/1999 | 1999-11-07 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
M23K | M23K-6 | AK.WAT6 | Certified Site-Existing | 62.5808 | -147.74 | 5510 | Susitna Watana | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/01/2013 | 2013-08-01 | 2015-02-19 | 2015-04-30 |  | NA | No | No | Yes | No
M24K | M24K-3-3 | M24K | Certified Site | 62.1067 | -146.175 | 2979 | Tolsona, Glenallen | Alaska | USA | State Patent or TA |  |  |  | 2014 |  | New Install |  |  | 7/25/2014 | 2014-08-01 | 2014-08-04 | 2014-08-19 | 2018-08-22 | 2020 | No | No | No | No
M25K | M25K-1 | HARP | Certified Site | 62.3987 | -145.1568 | 1906.17 | Gakona | Alaska | USA | Existing |  |  |  | 2015 | UAF Lease | New Install |  |  | 4/21/2015 | 2015-04-22 | 2015-04-22 | 2015-04-29 | 2016-08-26 | Adopted/Permanent | No | No | No | No
M26K | M26K_ME | M26K | Certified Site | 62.4013 | -142.9962 | 2920 | Devil's Mountian Lodge, Nebesna | Alaska | USA | Private |  |  |  | 2015 | Devil's Mountain Lodge | New Install |  |  | 07/12/2015 | 2015-07-13 | 2015-07-13 | 2015-07-16 | 2017-03-15 | 2020 | Yes | No | No | No
M27K | M27K-5 | M27K | Certified Site | 62.3579 | -141.878 | 5050 | Edge Creek | Alaska | USA | National Park Service |  |  |  | 2015 | NPS-Wrangell-St Elias | New Install |  |  | 07/10/2015 | 2015-07-12 | 2015-07-13 | 2015-07-16 | 2016-07-29 | 2020 | Yes | No | No | No
M28M | M28M-2 | CN.BVCY | Certified Site-Existing | 62.4141 | -140.8606 | 2237 | Beaver Creek Airport | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/14/2010 | 2010-08-14 | 2015-09-01 | 2015-09-01 |  | NA | No | No | No | No
M29M | M29M-1 | M29M | Certified Site | 62.4435 | -138.4624 | 4255 | Somme Creek | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2016 | Crown, BGAN @ 120 degrees | New Install |  | 7/24/2014 | 07/26/2016 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2018-08-28 | 2020 | Yes | No | No | No
M30M | M30M-T2 | M30M | Certified Site | 62.5763 | -136.7935 | 2564 | Minto | Yukon | Canada | First Nation |  |  |  | 2015 | Selkirk FN | New Install |  | 05/26/2015 | 10/18/2015 | 2015-10-18 | 2015-10-17 | 2015-10-18 | 2018-08-26 | 2020 | No | No | No | No
M31M | M31M-T3 | M31M | Certified Site | 62.2024 | -134.3906 | 2096 | Drury Creek Highway Camp | Yukon | Canada | Yukon Highways | Crown Land |  |  | 2015 |  | New Install |  | 8/4/2014 | 10/17/2015 | 2015-10-17 | 2015-12-03 | 2015-12-03 | 2015-10-17 | 2020 | No | No | No | No
N14K | N14K-1 | N14K | Certified Site | 59.9237 | -161.6852 | 68 | Kuskokwak Creek | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/28/2014 | 05/19/2017 | 2017-05-19 | 2017-05-20 | 2017-05-20 | 2017-05-19 | 2020 | Yes | No | No | No
N15K | N15K-1 | N15K | Certified Site | 60.1686 | -160.0921 | 1455 | Kwethluk River | Alaska | USA | FWS |  |  |  | 2017 | FWS-National Refuge System-Yukon Delta | New Install |  | 5/28/2014 | 05/20/2017 | 2017-05-20 | 2017-05-19 | 2017-05-19 | 2017-05-20 | 2020 | Yes | Yes | No | No
N16K | N16K-1 | N16K | Certified Site | 60.4742 | -158.769 | 1909 | Nishlik Lake | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR | New Install |  | 5/28/2014 | 5/28/2016 | 2016-05-28 | 2016-05-28 | 2016-05-28 | 2016-05-28 | 2020 | No | No | No | No
N17K | N17K-3.5 | N17K | Certified Site | 60.5269 | -157.1867 | 1148 | Nushagak Hills | Alaska | USA | State Patent or TA |  |  |  | 2017 |  | New Install |  |  | 05/13/2017 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2020 | Yes | Yes | No | No
N18K | N18K-3-1 | N18K | Certified Site | 60.6801 | -155.8897 | 1877 | Killae Creek | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 6/13/2015 | 2015-06-13 | 2015-06-14 | 2015-06-16 | 2017-04-05 | 2020 | Yes | No | No | No
N19K | N19K-6-HCL6 | N19K | Certified Site | 60.8132 | -154.4838 | 3753 | Bonanza Creek | Alaska | USA | State Patent or TA |  |  |  | 2015 |  | New Install |  |  | 6/12/2015 | 2015-06-13 | 2015-06-12 | 2015-06-16 | 2015-06-13 | 2020 | Planned | No | No | No
N20K | N20K-1 | N20K | Certified Site | 61.2002 | -152.2089 | 3228 | Ckakachatna River, Mt Spurr | Alaska | USA | State Patent or TA |  |  |  | 2015 | AVO site | New Install |  |  | 08/13/2015 | 2015-08-14 | 2005-02-11 | 2016-06-13 | 2018-06-26 | Leave Behind | Yes | No | Yes | Yes
N21K | N21K-1 | AK.SSN | Certified Site-Upgraded | 61.464 | -150.7444 | 4297 | Mount Susitna | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | Private | Station Upgrade |  |  | 08/05/2015 | 2008-08-15 | 2008-08-16 | 2015-02-20 |  | NA | No | No | Yes | No
N22K | N22K-3 | AK.RC01 | Certified Site-Upgraded | 61.0889 | -149.739 | 1281 | Rabbit Creek | Alaska | USA | Existing | Military |  |  | 2014 Existing | State Patent or TA, State Select, Native Select, Private | Station Upgrade |  |  | 08/07/1998 | 1998-08-07 | 2014-08-28 | 2014-09-04 |  | NA | No | No | Yes | No
N22K | N22K-4 | AT.PMR | Certified Site-Existing | 61.592 | -149.131 | 100 | Palmer | Alaska | USA | Existing | Private |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/15/2008 | 2008-08-15 | 2015-02-19 | 2015-04-30 |  | NA | No | No | No | No
N23K | N23K-1 | AK.KNK | Certified Site-Upgraded | 61.4131 | -148.4585 | 1978 | Knik | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing |  | Station Upgrade |  |  | 5/11/2015 | 2015-05-12 | 2010-06-14 | 2015-02-20 |  | NA | No | No | Yes | No
N24K | N24K-1 | AK.KLU | Certified Site-Existing | 61.493 | -145.9206 | 3784 | Klutina Pass | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | State Select | Accepted As Is |  |  | 07/13/2009 | 2009-07-13 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
N25K | N25K-3 | N25K | Certified Site | 61.6061 | -144.5982 | 3566 | Chitina, Valdez-Cordova | Alaska | USA | State Patent or TA |  |  |  | 2014 |  | New Install |  |  | 9/30/2014 | 2014-10-01 | 2014-10-02 | 2014-10-07 | 2018-08-25 | 2020 | No | No | No | No
N26K | N26K-1 | AK.MCAR | Certified Site-Upgraded | 61.3841 | -143.0219 | 1476 | McCarthy | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | WDL-National Park Service | Station Upgrade |  |  | 07/27/2015 | 2015-07-28 | 2013-01-02 | 2015-02-20 |  | NA | No | No | No | No
N28M | N28M-2 | CN.YUK3 | Certified Site-Existing | 61.7755 | -140.4595 | 6839 | Moose Peak | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/25/2010 | 2010-08-25 | 2015-09-01 | 2015-09-01 |  | NA | No | No | No | No
N29M | N29M-2 | CN.YUK4 | Certified Site-Existing | 61.4348 | -138.5463 | 6549 | Kluane Lake | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/29/2010 | 2010-08-29 | 2015-09-01 | 2015-09-01 |  | NA | No | No | No | No
N30M | N30M-T3 | N30M | Certified Site | 61.4593 | -137.0885 | 3086 | Aishihik Lake | Yukon | Canada | Crown Land |  |  |  | 2016 |  | New Install |  | 05/24/2015 | 05/01/2016 | 2016-05-01 | 2016-05-01 | 2016-04-30 | 2017-07-20 | 2020 | Yes | No | No | No
N31M | N31M-T2 | N31M | Certified Site | 61.4816 | -135.7798 | 2349 | Braeburn Lodge | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 8/4/2014 | 10/14/2015 | 2015-10-14 | 2015-10-20 | 2015-10-14 | 2018-03-27 | 2020 | No | No | No | No
N32M | N32M-T1 | N32M | Certified Site | 61.1512 | -133.0818 | 2676 | Quiet Lake | Yukon | Canada | Yukon Highways | Crown Land |  |  | 2016 | VSAT: Horizon-Trees at 14 degrees; Hills at 8 degrees | New Install |  | 8/26/2014 | 5/11/2016 | 2016-05-12 | 2016-05-26 | 2016-06-20 | 2017-09-20 | 2020 | No | No | No | No
O08K | O08K-1 | AK.SPIA | Certified Site-Upgraded | 57.1776 | -170.2455 | 276 | St. Paul Island | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | St. Paul (Village), FWS-National Refuge System | Station Upgrade |  |  | 09/19/2000 | 2000-09-19 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
O14K | O14K-1 | O14K | Certified Site | 59.2533 | -161.2638 | 423 | Tigyukauivet Mt. | Alaska | USA | BLM |  |  |  | 2017 |  | New Install |  | 5/28/2014 | 05/17/2017 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2020 | Yes | Yes | No | No
O15K | O15K-1 | O15K | Certified Site | 59.1767 | -159.8246 | 1000 | Ungalikthiuk River | Alaska | USA | FWS |  |  |  | 2017 |  | New Install |  | 5/28/2014 | 08/31/2017 | 2017-08-31 | 2017-08-31 | 2017-09-05 | 2018-10-18 | 2020 | Yes | No | No | No
O16K | O16K-1 | O16K | Certified Site | 59.5938 | -158.0932 | 3474 | Kokwok River, Bristol Bay | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install |  | 5/26/2014 | 5/27/2016 | 2016-05-27 | 2016-05-27 | 2016-05-27 | 2016-05-27 | 2020 | No | No | No | No
O17K | O17K-1 | O17K | Certified Site | 59.7733 | -157.0947 | 511 | Koliganek | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install |  |  | 5/29/2016 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2020 | No | No | No | No
O18K | O18K-JM | O18K | Certified Site | 59.8542 | -155.208 | 1775 | Koktuh Hill | Alaska | USA | State Patent or TA |  |  |  | 2015 | DNR | New Install |  | 4/2/2015 | 06/14/2015 | 2015-06-14 | 2015-06-16 | 2015-06-30 | 2018-10-18 | 2020 | Yes | No | No | No
O19K | O19K-2 | O19K | Certified Site | 60.1952 | -154.3201 | 315 | Port Alsworth | Alaska | USA | National Park Service |  |  |  | 2015 | Lake Clark | New Install |  | 4/2/2015 | 6/09/2015 | 2015-06-09 | 2015-06-10 | 2015-06-16 | 2018-09-25 | 2020 | Yes | No | Yes | No
O20K | O20K-1 | O20K | Certified Site | 60.0815 | -152.624 | 3002 | Slope Mountain | Alaska | USA | National Park Service |  |  |  | 2015 |  | New Install |  |  | 06/23/2015 | 2015-06-24 | 2015-06-30 | 2015-06-30 | 2015-06-24 | 2020 | No | No | No | No
O21K | O21K-1 | AK.CAPN | Certified Site-Upgraded | 60.7683 | -151.1539 | 164 | Soldotna | Alaska | USA | Existing | State Patent or TA |  |  | 2014 Existing | State Select, Private | Station Upgrade |  |  | 07/03/2013 | 2013-07-03 | 2014-06-10 | 2014-06-10 |  | NA | No | No | Yes | No
O22K | O22K-1 | O22K | Certified Site | 60.4814 | -149.7241 | 459 | Moose Pass | Alaska | USA | State Patent or TA |  |  |  | 2014 | Forest Service | New Install |  |  | 5/17/2014 | 2014-05-30 | 2014-06-02 | 2014-06-18 | 2018-08-21 | 2020 | Yes | No | No | No
O23K | O23K-2 | AK.GLI | Certified Site-Existing | 60.88 | -147.1 | 498 | Glacier Island | Alaska | USA | Existing | Forest Service |  |  | 2015 Existing |  | Accepted As Is |  |  | 07/27/2010 | 2010-07-26 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
O23K | O23K-1-AK.PWL | AK.PWL | Certified Site-Existing | 60.8584 | -148.3334 | 1804 | Port Wells | Alaska | USA | Existing | Forest Service |  |  | 2015 Existing |  | Accepted As Is |  |  | 09/13/2010 | 2010-09-13 | 2015-10-25 | 2015-10-26 |  | NA | No | No | Yes | No
O24K | O24K-1 | AK.EYAK | Certified Site-Upgraded | 60.5493 | -145.7479 | 453 | Cordova Ski Area | Alaska | USA | Existing | State Patent or TA |  |  | 2017 Existing | AEC site on Forest Service, Private. TA team constructed a new borehole on 9/29/2017 | Station Upgrade |  |  | 10/03/2002 | 2002-10-03 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
O25K | O25K-1 | AK.BMR | Certified Site-Upgraded | 60.9682 | -144.603 | 2679 | Bremner River | Alaska | USA | Existing | National Park Service |  |  | 2015 Existing |  | Station Upgrade |  |  | 08/07/2000 | 2000-08-07 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
O26K | O26K-1 | AK.CRQ | Certified Site-Existing | 60.75 | -143.09 | 3743 | Cirque | Alaska | USA | Existing | National Park Service |  |  | 2015 Existing |  | Accepted As Is |  |  | 06/20/2010 | 2010-06-20 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
O27K | O27K-1 | AK.CTG | Certified Site-Existing | 60.97 | -141.34 | 3743 | Chitna Glacier | Alaska | USA | Existing | National Park Service |  |  | 2015 Existing |  | Accepted As Is |  |  | 06/18/2015 | 2010-06-18 | 2015-02-19 | 2015-04-30 |  | NA | No | No | Yes | No
O28M | O28M-T1 | O28M | Certified Site | 60.7718 | -140.1906 | 8602 | Mt Upton, Kluane Nation Park Reserve | Yukon | Canada | Parks Canada |  |  |  | 2016 | VSAT: Horizon SE 7 degrees | New Install |  | 8/1/2014 | 7/17/2016 | 2016-07-17 | 2016-07-16 | 2016-07-16 | 2018-03-24 | 2020 | Yes | No | No | No
O29M | O29M-T3 | O29M | Certified Site | 60.3024 | -138.5755 | 4668 | Mount Kennedy | Yukon | Canada | Parks Canada |  |  |  | 2016 | VSAT: Horizon SE = 7 degrees | New Install |  |  | 07/15/2016 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2018-03-24 | 2020 | Yes | No | No | No
O29M | O29M-5 | CN.YUK8 | Certified Site-Existing | 61.2844 | -139.7646 | 2456 | Steele Glacier | Yukon | Canada | Existing | Parks Canada |  |  | 2016 Existing |  | Accepted As Is |  |  | 09/07/2012 | 2012-09-07 | 2016-05-27 | 2016-05-27 |  | NA | No | No | No | No
O29M | O29M-4 | CN.YUK6 | Certified Site-Existing | 60.9432 | -138.3626 | 6939 | Outpost Mtn | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/29/2010 | 2010-08-29 | 2015-09-01 | 2015-09-01 |  | NA | No | No | No | No
O30M | O30M-2 | CN.HYT | Certified Site-Existing | 60.83 | -137.5 | 32.51 | Pine Lake | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 09/15/1994 | 1994-09-15 | 2015-09-01 | 2015-09-01 |  | NA | No | No | No | No
O30N | O30N-T1 | O30N | Certified Site | 60.7704 | -136.0906 | 2692 | Mendenhall River NWTel Site | Yukon | Canada | Crown Land |  |  |  | 2016 |  | New Install | 09/24/2015 | 09/24/2015 | 05/12/2016 | 2016-05-13 | 2016-05-12 | 2016-05-12 | 2016-05-13 | 2020 | No | No | No | No
O31M | O31M-1 | CN.WHY | Certified Site-Existing | 60.66 | -134.88 | 3100 | Grey Mountain | Yukon | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 10/03/1994 | 1994-10-03 | 2015-04-21 | 2015-04-23 |  | NA | No | No | No | No
P08K | P08K-1 | P08K | Certified Site | 56.6011 | -169.5484 | 118 | St George Island | Alaska | USA | Native Patent or IC |  |  |  | 2017 | Located near clinic. Heavey equipment not avilable for borehole. | New Install |  |  | 10/09/2017 | 2017-10-09 | 2017-10-23 | 2017-12-22 | 2017-12-22 | 2020 | No | No | No | No
P16K | P16K-1 | P16K | Certified Site | 59.0314 | -157.9906 | 282 | Nushagak River | Alaska | USA | State Patent or TA |  |  |  | 2016 | DNR | New Install |  | 5/29/2014 | 5/26/2016 | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2020 | No | No | No | No
P17K | P17K-4-1 | P17K | Certified Site | 59.1953 | -156.4394 | 300 | Kvichak River | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install |  |  | 5/31/2016 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-06-07 | 2020 | Yes | No | No | No
P18K | P18K-1 | P18K | Certified Site | 59.3922 | -155.2292 | 2038 | Big Mountain | Alaska | USA | State Patent or TA |  |  |  | 2015 | State Patent or TA | New Install |  |  | 6/15/2015 | 2015-06-16 | 2015-10-11 | 2015-10-11 | 2017-10-11 | Leave Behind | Planned | No | Yes | No
P19K | P19K-1 | P19K | Certified Site | 59.65 | -153.23 | 273 | Oil Point | Alaska | USA | Native Patent or IC |  |  |  | 2015 |  | New Install |  |  | 06/24/2015 | 2015-06-25 | 2015-06-24 | 2015-06-30 | 2017-08-07 | Leave Behind | Yes | No | Yes | No
P20K | P20K-1 | AK.HOM | Certified Site-Upgraded | 59.6578 | -151.6494 | 721 | Anchor Point | Alaska | USA | Existing | State Patent or TA |  |  | 2014 Existing | State Select, Private | Station Upgrade |  |  | 06/18/2009 | 2009-06-18 | 2014-08-21 | 2014-08-22 |  | NA | No | No | Yes | No
P21K | P21K-6 | AK.BRSE | Certified Site-Existing | 59.7417 | -150.7414 | 1770 | Bradley Lake South | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | UAF site | Accepted As Is |  |  | 07/01/2013 | 2013-07-01 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
P22K | P22K-1 | AK.SWD | Certified Site-Existing | 60.1049 | -149.4507 | 262 | Seward | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | State Select, Private | Accepted As Is |  |  | 06/04/2001 | 2001-06-04 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
P23K | P23K-1 | P23K | Certified Site | 59.9979 | -147.4031 | 941 | Montague Island | Alaska | USA | Existing | Native Patent or IC |  |  | 2016 | Forest Service | New Install |  |  | 5/23/2016 | 2016-05-23 | 2016-05-23 | 2016-05-23 | 2018-09-14 | 2020 | Yes | No | No | No
P25K | P25K-1 | AK.KAI | Certified Site-Upgraded | 59.9273 | -144.417 | 997 | Kayak Island | Alaska | USA | Existing | Forest Service |  |  | 2016 Existing | FWS-National Refuge System | Station Upgrade |  |  | 8/3/1982 | 1982-08-03 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
P26K | P26K-1 | AK.BGLC | Certified Site-Existing | 60.121 | -143.2821 | 49 | Bering Glacier BLM Camp | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | FWS-National Refuge System | Accepted As Is |  |  | 07/16/2005 | 2005-07-16 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
P27K | P27K-1 | AK.MESA | Certified Site-Upgraded | 60.17 | -141.9485 | 6418 | Mesa | Alaska | USA | Existing | National Park Service |  |  | 2015 Existing |  | Station Upgrade |  |  | 08/01/2006 | 2006-08-01 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
P28K | P28K-2 | AK.PNL | Certified Site-Upgraded | 59.6659 | -139.4036 | 1800 | Yukatat Peninsula | Alaska | USA | Existing | Forest Service |  |  | 2015 Existing |  | Station Upgrade |  |  | 09/02/1974 | 1974-09-02 | 2015-10-25 | 2015-10-26 |  | NA | No | No | No | No
P28K | P28K-1 | AK.PIN | Certified Site-Upgraded | 60.0967 | -140.2566 | 2696 | Pinnacle | Alaska | USA | Existing | National Park Service |  |  | 2016 Existing |  | Station Upgrade |  |  | 08/13/1996 | 1996-08-13 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
P29M | P29M-T1 | P29M | Certified Site | 59.6303 | -137.7381 | 2227 | Windy Craggy | British Columbia | Canada | BC Parks |  |  |  | 2016 | VSAT: Horizon SE 3 degrees | New Install |  | 7/22/2014 | 07/15/2016 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2017-09-19 | 2020 | Yes | No | No | No
P30M | P30M-T1 | P30M | Certified Site | 60.1218 | -136.9589 | 2897 | MDFC GPS Site, Million Dollar Falls | Yukon | Canada | Crown Land |  |  |  | 2016 | VSAT: Horizon SE 12 degrees | New Install |  | 5/31/2014 | 04/30/2016 | 2016-04-30 | 2016-04-30 | 2016-06-20 | 2016-10-01 | 2020 | No | No | No | No
P32M | P32M-T1 | P32M | Certified Site | 59.5898 | -133.7146 | 2601 | Atlin | British Columbia | Canada | Crown Land |  |  |  | 2016 |  | New Install |  | 7/19/2014 | 05/03/2016 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | Adopted/Permanent | No | No | No | No
P33M | P33M-T3 | P33M | Certified Site | 60.2114 | -132.8174 | 3496 | Teslin | Yukon | Canada | Crown Land | Yukon Highways |  |  | 2015 |  | New Install |  | 05/02/2015 | 10/15/2015 | 2015-10-15 | 2015-10-15 | 2015-10-15 | 2016-06-04 | 2020 | No | No | No | No
Q16K | Q16K-1 | Q16K | Certified Site | 58.6774 | -156.6556 | 72 | King Salmon | Alaska | USA | AKDOT |  |  |  | 2016 |  | New Install |  | 01/28/2016 | 06/02/2016 | 2016-06-09 | 2016-06-09 | 2016-06-09 | 2016-06-09 | 2020 | No | No | Yes | No
Q17K | Q17K-2 | Q17K | Certified Site | 58.2637 | -155.8865 | 3842 | Contact Creek, Katmai | Alaska | USA | National Park Service |  |  |  | 2016 | NPS-Wilderness Desig | New Install |  |  | 06/05/2016 | 2016-06-05 | 2016-06-05 | 2016-06-05 | 2016-06-05 | Leave Behind | Planned | No | No | No
Q18K | Q18K-3 | Q18K | Certified Site | 58.6483 | -155.0081 | 4101 | Katmai Hardscrabble Creek | Alaska | USA | National Park Service |  |  |  | 2016 | WDL-NPS-Wilderness Desig | New Install |  |  | 6/03/2016 | 2016-06-03 | 2016-06-02 | 2016-06-02 | 2016-06-03 | Leave Behind | Planned | No | No | No
Q19K | Q19K-1 | Q19K | Certified Site | 58.9287 | -153.6446 | 1950 | Cape Douglas | Alaska | USA | National Park Service |  |  |  | 2015 |  | New Install |  |  | 08/14/2015 | 2015-08-15 | 2015-08-16 | 2015-08-15 | 2015-08-15 | 2020 | Planned | No | No | No
Q20K | Q20K | Q20K | Certified Site | 58.6097 | -152.3942 | 590 | Shuayk Island | Alaska | USA | Existing |  |  |  | 2016 |  | New Install |  |  | 05/24/2016 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | Leave Behind | No | No | No | No
Q23K | Q23K-1 | Q23K | Certified Site | 59.4296 | -146.3499 | 151 | Middleton Island | Alaska | USA | Native Patent or IC |  |  |  | 2014 | FWS | New Install |  |  | 8/15/2014 | 2014-08-17 | 2014-08-19 | 2014-08-16 | 2016-03-31 | 2020 | No | No | Yes | No
Q29K | Q29K-2 | AK.DCPH | Certified Site-Existing | 59.0912 | -138.2136 | 2198 | Deception Hills | Alaska | USA | Existing | National Park Service |  |  | 2015 Existing |  | Accepted As Is |  |  | 08/03/2002 | 2002-08-03 | 2015-04-30 | 2015-04-30 |  | NA | No | No | Yes | No
Q30M | Q30M-1 | CN.PLBC | Certified Site-Existing | 59.455 | -136.3659 | 1984 | Pleasant Camp | British Columbia | Canada | Existing |  |  |  | 2015 Existing |  | Accepted As Is |  |  | 09/03/2005 | 2005-09-03 | 2016-05-19 | 2016-10-03 |  | NA | No | No | No | No
Q31K | Q31K-1 | AT.SKAG | Certified Site-Existing | 59.4601 | -135.329 | 426 | Tulsequah | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | State Select, Private | Accepted As Is |  |  | 10/13/2004 | 2004-10-13 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
Q32M | Q32M-T2 | Q32M | Certified Site | 58.9601 | -132.2691 | 6400 | Nakina River | British Columbia | Canada | Crown Land |  |  |  | 2016 | VSAT: Horizon SE 2 degrees | New Install |  | 7/21/2014 | 07/24/2016 | 2016-07-24 | 2016-08-22 | 2016-08-22 | 2018-06-23 | 2020 | Yes | No | No | No
R16K | R16K-1 | R16K | Certified Site | 57.5673 | -157.5742 | 124 | Pilot Point | Alaska | USA | Private |  |  |  | 2016 | Private | New Install |  |  | 06/08/2016 | 2016-06-08 | 2016-06-09 | 2016-06-20 | 2016-06-08 | 2020 | No | No | Planned | No
R17K | R17L | R17L | Certified Site-Upgraded | 57.6313 | -156.3599 | 1719 | Mt. Peulik Volcano | Alaska | USA | FWS |  |  |  | 2016 | Station replaces closed R17K | Station Upgrade |  |  | 06/22/2018 | 2018-06-23 | 2018-06-29 | 2018-07-02 | 2018-06-23 | Leave Behind | Yes | No | Yes | No
R18K | R18K-1 | R18K | Certified Site | 57.5665 | -154.4524 | 131 | Karluk | Alaska | USA | AKDOT |  |  |  | 2017 | Karlu Village, Private | New Install |  | 8/29/2014 | 04/25/2017 | 2017-04-26 | 2017-06-18 | 2017-06-18 | 2018-05-25 | 2020 | Yes | No | Yes | No
R19K | R19K-3 | II.KDAK | Certified Site-Existing | 57.7828 | -152.5835 | 141 |  | Alaska | USA | Existing | Bureau of Land Management |  |  | 2015 Existing |  | Accepted As Is |  |  | 06/09/1997 | 1997-06-09 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
R31K | R31K-1 | R31K | Certified Site | 58.4133 | -135.7398 | 49 | Gustavus City Hall | Alaska | USA | State Patent or TA | Private |  |  | 2016 | Private | New Install |  | 9/18/2014 | 8/22/2016 | 2016-09-12 | 2016-09-12 | 2016-09-12 | 2018-09-25 | 2020 | Yes | No | No | No
R32K | R32K-2 | R32K | Certified Site | 58.2747 | -134.5181 | 1266 | Eagle Crest Ski Area | Alaska | USA | Private |  |  |  | 2016 |  | New Install |  |  | 08/14/2016 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2018-09-24 | 2020 | Yes | No | No | No
R33M | R33M-T1 | R33M | Certified Site | 59.3946 | -130.9673 | 4714 | Jennings River | British Columbia | Canada | Crown Land |  |  |  | 2016 | VSAT: Horizon SE 1 degree | New Install |  | 7/20/2014 | 07/21/2016 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2017-04-04 | 2020 | Yes | No | No | No
R35M | R35M-1-CN.DLBC | CN.DLBC | Certified Site-Existing | 58.4372 | -130.0272 | 978 | Dease Lake | British Columbia | Canada | Existing |  |  |  | 2016 Existing |  | Accepted As Is |  |  | 09/28/1994 | 1994-09-28 | 2016-05-27 | 2016-05-27 |  | NA | No | No | No | No
S12K | S12K-1 | S12K | Certified Site | 55.703 | -162.067 | 1349 | Black Hill | Alaska | USA | State Patent or TA |  |  |  | 2016 |  | New Install |  |  | 6/11/2016 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2017-06-30 | Leave Behind | No | No | Yes | No
S13K | S13K-1 | AT.SDPT | Certified Site-Existing | 55.3491 | -160.4766 | 230 | Sand Point | Alaska | USA | Existing | Native Patent or IC |  |  | 2016 Existing | FWS-National Refuge System | Accepted As Is |  |  | 8/28/2002 | 2002-08-28 | 2002-08-29 | 2015-02-20 |  | NA | No | No | No | No
S14K | S14K-1 | S14K | Certified Site | 56.2848 | -159.5532 | 3474 | Mount Veniaminof, Fog Glacier | Alaska | USA | FWS |  |  |  | 2016 | FWS-National Refuge System | New Install |  |  | 06/12/2016 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2018-07-11 | Leave Behind | Yes | No | No | No
S15K | S15K-1 | S15K | Certified Site | 56.3058 | -158.54 | 56 | Chignik | Alaska | USA | Private |  |  |  | 2017 |  | New Install |  |  | 07/11/2018 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2020 | No | No | No | No
S15K | S15K-2 | AT.CHGN | Certified Site-Existing | 56.3014 | -158.4142 | 433 | Chignik | Alaska | USA | Existing | Native Patent or IC |  |  | 2016 Existing | Chignik (Village), FWS-National Refuge System, Private | Accepted As Is |  |  | 8/10/2011 | 2011-08-10 | 2011-08-11 | 2015-02-20 |  | NA | No | No | Planned | No
S18K | S18K-2 | AK.SII | Certified Site-Existing | 56.56 | -154.1819 | 492 | Sitkinak Island Coast Guard | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | FWS-National Refuge System | Accepted As Is |  |  | 08/29/2007 | 2007-08-29 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
S19K | S19K-4 | S19K | Certified Site | 57.2225 | -153.2875 | 154 | Old Harbor | Alaska | USA | Private |  |  |  | 2019 |  | New Install |  |  | 05/24/2018 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-24 | NA | No | No | Yes | No
S19K | S19K-3 | AT.OHAK | Certified Site-Existing | 57.2225 | -153.2875 | 120 | Old Harbor | Alaska | USA | Existing | Private |  |  | 2016 Existing | Old Harbor (Village), FWS-National Refuge System | Accepted As Is |  |  | 6/23/2006 | 2006-06-23 | 2015-02-19 | 2015-02-20 | 2018-05-24 | NA | No | No | Yes | No
S31K | S31K-2 | S31K | Certified Site | 57.9616 | -136.232 | 112 | Perlican | Alaska | USA | Private |  |  |  | 2016 |  | New Install |  | 9/21/2016 | 9/21/2016 | 2016-09-21 | 2016-10-08 | 2016-10-14 | 2016-10-08 | 2020 | Yes | No | Yes | No
S32K | S32K-2 | S32K | Certified Site | 57.4688 | -134.5763 | 85 | Killisnoo Island | Alaska | USA | Private |  |  |  | 2016 | Private | New Install |  | 9/14/2014 | 09/09/2016 | 2016-09-09 | 2016-08-24 | 2016-08-24 | 2018-09-27 | 2020 | No | No | No | No
S34M | S34M-T1 | S34M | Certified Site | 57.9128 | -131.1312 | 978 | Telegraph Creek | British Columbia | Canada | Lake District Maintenance |  |  |  | 2016 | DSL, Alternate VSAT: Horizon SE 10 degrees | New Install |  | 8/28/2014 | 05/05/2016 | 2016-05-06 | 2016-05-06 | 2016-04-30 | 2016-10-05 | 2020 | No | No | No | No
T09K | T09K-2 | AK.UNV | Certified Site-Upgraded | 53.8465 | -166.502 | 230 | Unalaska | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | FWS-National Refuge System, Private | Station Upgrade |  |  | 02/19/1999 | 1999-02-19 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
T10K | T10K-2 | AK.FALS | Certified Site-Existing | 54.8573 | -163.4155 | 51 | False Pass | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | False Pass (Village), FWS-National Refuge System | Accepted As Is |  |  | 06/19/2002 | 2002-06-19 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
T17K | T17K-2 | AK.CHI | Certified Site-Existing | 55.8225 | -155.621 | 656 | Chirikof Island | Alaska | USA | Existing | Fish and Wildlife Service |  |  | 2015 Existing | WDL-FWS-National Refuge System | Accepted As Is |  |  | 09/15/2008 | 2008-09-15 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
T32K | T32K-1 | AT.SIT | Certified Site-Existing | 57.06 | -135.32 | 169 | Sitka | Alaska | USA | Existing | State Patent or TA |  |  | 2015 Existing | Forest Service, National Park Service, Private | Accepted As Is |  |  | 09/11/1999 | 1999-09-11 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
T33K | T33K-2 | T33K | Certified Site | 56.8144 | -132.9524 | 72 | Petersburg | Alaska | USA | Private |  |  |  | 2016 |  | New Install |  |  | 08/16/2016 | 2016-08-16 | 2016-08-16 | 2016-08-16 | 2018-09-27 | 2020 | Yes | No | No | No
T34K | T34K-2 | US.WRAK | Certified Site-Existing | 56.4191 | -132.3466 | 275 | Wrangell Island | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | State Patent or TA, Forest Service. Global Seismic Network Station. | Accepted As Is |  |  | 08/28/2006 | 2006-08-28 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
T35M | T35M-T2 | T35M | Certified Site | 56.9811 | -130.2496 | 2000 | Bob Quinn LDM Yard | British Columbia | Canada | Lake District Maintenance |  |  |  | 2016 | VSAT: Horizon SE 13 degrees, XPlorNet ISP in use by LDM on site | New Install |  | 8/29/2014 | 05/08/2016 | 2016-05-08 | 407755 | 2016-05-27 | 2016-05-13 | 2020 | No | No | No | No
U06K | U06K-3 | AK.NIKH | Certified Site-Existing | 52.9732 | -168.853 | 656 | Nikolski High Hill | Alaska | USA | Existing | Military |  |  | 2015 Existing | MIL-Dept of Air Force, FWS-National Refuge System, Native Patent or IC, Nikolski (Village) | Accepted As Is |  |  | 06/21/2007 | 2007-06-21 | 2015-02-19 | 2015-04-30 |  | NA | No | No | Yes | No
U13K | U13K-1 | AK.CHN | Certified Site-Existing | 54.831 | -159.5895 | 275 | Unga | Alaska | USA | Existing | Fish and Wildlife Service |  |  | 2015 Existing | FWS-National Refuge System | Accepted As Is |  |  | 06/27/2013 | 2013-06-27 | 2015-02-19 | 2015-02-20 |  | NA | No | No | Yes | No
U33K | U33K-1 | U33K | Certified Site | 56.1146 | -133.121 | 36 | Whale Pass | Alaska | USA | State Patent or TA | Private |  |  | 2016 | State Patent or TA, Forest Service | New Install |  | 9/17/2014 | 08/21/2016 | 2016-09-14 | 2016-09-15 | 2016-09-15 | 2016-09-14 | 2020 | Yes | No | No | No
U35K | U35K-2 | U35K | Certified Site | 55.9155 | -130.0257 | 56 | Hyder Community Center | Alaska | USA | State Patent or TA | Private |  |  | 2016 | Forest Service, Private. Contact the Hyder Communicty Center/Library prior to visit to secure building access. Carol Denton (250) 636-9148 (w) and (250) 636-2859 or the Library at (250) 636-9169. | New Install |  | 9/16/2014 | 05/01/2016 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2018-07-18 | 2020 | No | No | No | No
V34K | V34K-4 | AT.CRAG | Certified Site-Existing | 55.47 | -133.12 | 25 | Craig | Alaska | USA | Existing | Native Patent or IC |  |  | 2015 Existing | Craig (Village of), Forest Service | Accepted As Is |  |  | 12/10/2004 | 2014-12-10 | 2015-02-19 | 2015-02-20 |  | NA | No | No | No | No
V35K | V35K-1 | V35K | Certified Site | 55.3279 | -131.615 | 210 | Ketchikan | Alaska | USA | State Patent or TA |  |  |  | 2016 | Private | New Install |  | 9/16/2014 | 08/17/2016 | 2016-08-18 | 2016-08-18 | 2016-08-18 | 2018-09-28 | 2020 | Yes | No | No | No